## CRM Rollout
Category | Requirement | Priority | Owner
Lead Management | Replace spreadsheet-based lead tracking with centralized CRM records | High | Sales Ops
Pipeline Visibility | Provide regional pipeline dashboard for sales managers | High | Revenue Operations
Marketing Handoff | Define automated MQL to SQL handoff workflow | Medium | Marketing Ops
Finance Integration | Integrate CRM opportunity data with finance reporting | High | Finance Systems

## Risks
Risk | Mitigation
Low adoption by sales team | Create role-based training and champion network
Data quality issues | Run data cleanup before migration
Integration delay | Prioritize minimum viable finance export in phase one